## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
Project ID: Car Servicing | <Batch code/project id> |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FEA 1.1 | 1 | Creating Home Page with some information why Blood donation is required and options for login, registration & Master page | Ravi | 10 | 9 | 1 |  |  |  |  | Completed
FEA 1.2 | 2 | User able to save themselves by registering their details by filling mandatory fields and post-success registration redirected to Login page | Ganesh | 7 | 6 | 1 |  |  |  |  | Completed
FEA 1.3 | 3 | User able to Login by providing credentials and redirecting to Home page post-success login by validating user credentials | Philomina | 6 | 5 | 1 |  |  |  |  | Completed
FEA 2.1 | 4 | Ability of the system to allow user to request for the required blood and display the matching results | Philomina | 7 |  | 7 |  |  |  |  | Completed
FEA 2.2 | 5 | If no match found for user blood requirements, user can post his blood requirements on Home page for donation by filling mandatory details | Ganesh | 5 |  | 5 |  |  |  |  | Completed
FEA 3.1 | 6 | Ability of the system to store the details of blood donated by a user who is willing to donate their blood and selecting hospital with available slots to donate blood | Ravi | 8 |  | 8 |  |  |  |  | Completed
FEA 3.2 | 7 | Post-success blood donation user can share their Experience about hospital and display those experiences on Home page | Ravi | 6 |  | 6 |  |  |  |  | Completed
FEA 4.1 | 8 | Create a page to have information about Instructions for Donating blood & link to donate blood | Ravi | 2 |  | 2 |  |  |  |  | Completed
|  | Total |  | 51 | 20 | 31 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FEA 4.2 | 1 | Provide a FAQ page for blood donation for the user to view & Raise a query for any clarifications. | Philomina | 3 | 3 | [5 empty] | Completed
FEA 4.3 | 2 | Send a notification message to the user who have donated the blood before 3 months to donate blood again & Query status | Ganesh | 3 | 3 | [5 empty] | Completed
FEA 4.4 | 3 | Send a notifcation message to user with that particular blood type to donate blood when there is requirement. | Ravi | 2 | 2 | [5 empty] | Completed
|  | Total |  | 8 | 8 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A